## Document Control
Document Control
Contact(s) for inquirries and proposed changes
Name | Title
Yi Yi Htun | QA
Revision History
Name | Date | Version | Reason for Changes/ Comments
Yi Yi | 21/05/2025 | VR 0.1 | Template initial draft
|  | VR 1.0 | Baseline
Reviewers
Name | Title | Date | Evidence
Project Manager
Signed-Off
Name | Title | Date | Evidence

## Test Plan
Introduction: | To define testing strategy for inventory service, coupon service, payment service, delivery service
Objectives: | Ensure that all functionalities meet specified requirements
Test Scope: | This test covers functionalities, but not system security
Date: |  |  | Updated on:
Test Items | Test Environment & Tools | Test Types | Test Strategy and Approach | Entry Criteria | Exit Criteria | Deliverables | Start Date | End Date | Assignee | KPIs | Notes
| Dev & Server | functional | unit testing | all functional requirements must be finalized and approved | at least 95% of the planned test cases must be executed | document listing all test cases |  |  |  | test case execution rate: executed test cases/total test cases x 100
| UAT | functional | integration testing | test cases must be written, reviewed and approved | a mimimum of 90% of executed test cases must pass | report summarizing outcomes of test case executions |  |  |  | pass rate: passed test cases/executed test cases x 100
Test Plan Team
Name | Role | Responsibilities
Yi Yi Htun | QA | test functionality

## Test Scenario
Test Scenarios from BRD and FSD:
Checklist
| Test scenario ID |  |  | Test Objective/Test scenarios
Module1 : Inventory Service | FUN_INV_ | 1 | FUN_INV_1 | Verify adding a new product to inventory | FUN_INV_1 | TRUE
| FUN_INV_ | 2 | FUN_INV_2 | Verify that stock quantity can be modified correctly (increase/decrease). | FUN_INV_2 | FALSE
| FUN_INV_ | 3 | FUN_INV_3 | Validate that changes are reflected in real-time inventory records. | FUN_INV_3 | FALSE
| FUN_INV_ | 4 | FUN_INV_4 | Verify product details in inventory | FUN_INV_4 | FALSE
| FUN_INV_ | 5 | FUN_INV_5 | Validate removal of a product from inventory | FUN_INV_5 | FALSE
| FUN_INV_ | 6 | FUN_INV_6 | Verify inventory adjustment operations | FUN_INV_6 | FALSE
| FUN_INV_ | 7 | FUN_INV_7 | Verify inventory is decremented only after order confirmation | FUN_INV_7 | FALSE
| FUN_INV_ | 8 | FUN_INV_8 | Ensure inventory rollback if payment or downstream service fails | FUN_INV_8 | FALSE
| NON-FUN_INV_ | 9 | NON-FUN_INV_9 | Verify a high volume of simultaneous inventory update requests from multiple shops. | NON-FUN_INV_9 | FALSE
| NON-FUN_INV_ | 10 | NON-FUN_INV_10 | Verify system performance under delivery tracking load | NON-FUN_INV_10 | FALSE
Module2 : Coupon Service | FUN_COUPON_ | 11 | FUN_COUPON_11 | Verify that users can successfully collect vouchers from the homepage, campaign banners, product pages, or promotional pop-ups. | FUN_COUPON_11 | FALSE
| FUN_COUPON_ | 12 | FUN_COUPON_12 | Verify that users receive a coupon/voucher immediately after following a shop, if such a promotion is active. | FUN_COUPON_12 | FALSE
| FUN_COUPON_ | 13 | FUN_COUPON_13 | Verify that claimed vouchers are immediately visible and usable from the user's voucher wallet. | FUN_COUPON_13 | FALSE
| FUN_COUPON_ | 14 | FUN_COUPON_14 | Verify special welcome voucher for new users | FUN_COUPON_14 | FALSE
| FUN_COUPON_ | 15 | FUN_COUPON_15 | Verify frontend display of voucher conditions matches backend configuration e.g Min. Spend THB 1,500 • Valid Until May 31, 2025 • LazMall Only | FUN_COUPON_15 | FALSE
| FUN_COUPON_ | 16 | FUN_COUPON_16 | Validate that a valid voucher/Coupon code is successfully applied and the discount is reflected in the total price | FUN_COUPON_16 | FALSE
| FUN_COUPON_ | 17 | FUN_COUPON_17 | Validate that free shipping vouchers waive shipping fees under specified conditions (e.g., minimum purchase amount, eligible regions). | FUN_COUPON_17 | FALSE
| FUN_COUPON_ | 18 | FUN_COUPON_18 | Validate that an expired voucher code is rejected with an appropriate error message | FUN_COUPON_18 | FALSE
| FUN_COUPON_ | 19 | FUN_COUPON_19 | Verify that such vouchers are only applicable to products belonging to the respective store or seller during checkout. | FUN_COUPON_19 | FALSE
| FUN_COUPON_ | 20 | FUN_COUPON_20 | Ensure that eligible coupons can be manually by keyin the coupon code to the order. | FUN_COUPON_20 | FALSE
| FUN_COUPON_ | 21 | FUN_COUPON_21 | Verify that removing an applied voucher restores it to the user's voucher wallet | FUN_COUPON_21 | FALSE
| FUN_COUPON_ | 22 | FUN_COUPON_22 | Validate that when a user removes an existing voucher and applies a new one, the updated voucher is correctly applied and reflected in the order summary. | FUN_COUPON_22 | FALSE
| FUN_COUPON_ | 23 | FUN_COUPON_23 | Confirm that the correct discount or benefit is reflected in the order summary. | FUN_COUPON_23 | FALSE
| FUN_COUPON_ | 24 | FUN_COUPON_24 | Ensure that once a coupon has expired, it is automatically removed from the list of selectable vouchers in the user's voucher wallet or checkout screen | FUN_COUPON_24 | FALSE
| Non-FUN_COUPON_ | 25 | Non-FUN_COUPON_25 | Verify for high load of Coupon (e.g., 11.11 sales event/ 10:10 sales) | Non-FUN_COUPON_25 | FALSE
| Non-FUN_COUPON_ | 26 | Non-FUN_COUPON_26 | Simulate 5,000 users attempting to redeem the same coupon code concurrently to validate system performance and redemption limits. | Non-FUN_COUPON_26 | FALSE
Modue3 : Payment Service | FUN_PAYMENT_ | 27 | FUN_PAYMENT_27 | Verify successful payment processing with valid card | FUN_PAYMENT_27 | FALSE
| FUN_PAYMENT_ | 28 | FUN_PAYMENT_28 | Validate error on invalid card details | FUN_PAYMENT_28 | FALSE
| FUN_PAYMENT_ | 29 | FUN_PAYMENT_29 | Verify duplicating transaction (Ensure no double charge on repeat click) | FUN_PAYMENT_29 | FALSE
| FUN_PAYMENT_ | 30 | FUN_PAYMENT_30 | Allow retry if first attempt fails due to timeout | FUN_PAYMENT_30 | FALSE
| FUN_PAYMENT_ | 31 | FUN_PAYMENT_31 | Verify refund processed correctly | FUN_PAYMENT_31 | FALSE
| FUN_PAYMENT_ | 32 | FUN_PAYMENT_32 | Verify Payment Summary or Checkout Page Displays Correct Data | FUN_PAYMENT_32 | FALSE
| FUN_PAYMENT_ | 33 | FUN_PAYMENT_33 | Verify All Available Payment Methods Are Displayed in the Drop-Down List | FUN_PAYMENT_33 | FALSE
| FUN_PAYMENT_ | 34 | FUN_PAYMENT_34 | Verify Mobile Banking Option Supports All Thai Banks | FUN_PAYMENT_34 | FALSE
| FUN_PAYMENT_ | 35 | FUN_PAYMENT_35 | Verify QR PromptPay Payment Flow | FUN_PAYMENT_35 | FALSE
| FUN_PAYMENT_ | 36 | FUN_PAYMENT_36 | Verify Payment Using Lazada Wallet | FUN_PAYMENT_36 | FALSE
| FUN_PAYMENT_ | 37 | FUN_PAYMENT_37 | Verify Payment via TrueMoney | FUN_PAYMENT_37 | FALSE
| FUN_PAYMENT_ | 38 | FUN_PAYMENT_38 | Verify LINE Pay Integration | FUN_PAYMENT_38 | FALSE
| FUN_PAYMENT_ | 39 | FUN_PAYMENT_39 | Verify Cash on Delivery Option | FUN_PAYMENT_39 | FALSE
| FUN_PAYMENT_ | 40 | FUN_PAYMENT_40 | Verify Cash on Delivery | FUN_PAYMENT_40 | FALSE
| FUN_PAYMENT_ | 41 | FUN_PAYMENT_41 | Verify Receipt Is Successfully Sent to the Use | FUN_PAYMENT_41 | FALSE
| FUN_PAYMENT_ | 42 | FUN_PAYMENT_42 | Attempt payment with expired card | FUN_PAYMENT_42 | FALSE
| FUN_PAYMENT_ | 43 | FUN_PAYMENT_43 | Leave mandatory field empty and try to proceed | FUN_PAYMENT_43 | FALSE
| FUN_PAYMENT_ | 44 | FUN_PAYMENT_44 | Try payment with negative amount | FUN_PAYMENT_44 | FALSE
| FUN_PAYMENT_ | 45 | FUN_PAYMENT_45 | Try payment with zero amount | FUN_PAYMENT_45 | FALSE
| FUN_PAYMENT_ | 46 | FUN_PAYMENT_46 | Validate session expire before submitting payment | FUN_PAYMENT_46 | FALSE
| FUN_PAYMENT_ | 47 | FUN_PAYMENT_47 | Submit payment when payment service is down | FUN_PAYMENT_47 | FALSE
| NON-FUN_PAYMENT_ | 48 | NON-FUN_PAYMENT_48 | Verify that the application displays a clear error or retries the request appropriately when the payment gateway times out (e.g., after 10 seconds of no response). | NON-FUN_PAYMENT_48 | FALSE
| NON-FUN_PAYMENT_ | 49 | NON-FUN_PAYMENT_49 | Ensure that the payment service can handle a high number of concurrent payment attempts without race conditions or double charges. | NON-FUN_PAYMENT_49 | FALSE
| NON-FUN_PAYMENT_ | 50 | NON-FUN_PAYMENT_50 | Conduct load testing to validate that the payment service can process a high volume of requests (e.g., 1,000 transactions per minute) | NON-FUN_PAYMENT_50 | FALSE
| NON-FUN_PAYMENT_ | 51 | NON-FUN_PAYMENT_51 | Verify Security - no card inforamtion are stored in the system | NON-FUN_PAYMENT_51 | FALSE
Module 4: Delivery Service | FUN_DEL | 52 | FUN_DEL52 | Verify delivery date and address are correct after made the payment | FUN_DEL52 | FALSE
| FUN_DEL | 53 | FUN_DEL53 | Allow users to modify the delivery address before the order is dispatched. | FUN_DEL53 | FALSE
| FUN_DEL | 54 | FUN_DEL54 | Ensure that once an order is confirmed, a delivery partner is assigned correctly. | FUN_DEL54 | FALSE
| FUN_DEL | 55 | FUN_DEL55 | Validate real-time tracking updates (e.g., Shipped, In Transit, Delivered). | FUN_DEL55 | FALSE
| FUN_DEL | 56 | FUN_DEL56 | Ensure the system manages failed deliveries (e.g., customer not available) and allows rescheduling. | FUN_DEL56 | FALSE
| FUN_DEL | 57 | FUN_DEL57 | Verify the Notification of Delivery Progress (e.g SMS, push, or email notifications are sent for each status update.) | FUN_DEL57 | FALSE
| FUN_DEL | 58 | FUN_DEL58 | Verify that cancelling an order cancels the associated delivery and updates logistics records. | FUN_DEL58 | FALSE
| FUN_DEL | 59 | FUN_DEL59 | Verify that deliver pick up for return items | FUN_DEL59 | FALSE
| FUN_DEL | 60 | FUN_DEL60 | Verify Priority 24H Delivery Option | FUN_DEL60 | FALSE
| FUN_DEL | 61 | FUN_DEL61 | Check with Seller to follow up on the delivery process | FUN_DEL61 | FALSE
| FUN_DEL | 62 | FUN_DEL62 | Validate for wrong address : user enters an address with missing fields (e.g., no postal code, symbols in street name). | FUN_DEL62 | FALSE
| FUN_DEL | 63 | FUN_DEL63 | Verify for Changing Address After Shipment | FUN_DEL63 | FALSE
| NON-FUN_DEL | 64 | NON-FUN_DEL64 | Test if delivery API performs well under 1000+ concurrent delivery requests | NON-FUN_DEL64 | FALSE
| NON-FUN_DEL | 65 | NON-FUN_DEL65 | Verify that 1000+ delivery status push noti are sent at a time | NON-FUN_DEL65 | FALSE

## Test Case
Test Cases
Project Name |  | e-commerce service
Module Name |  | Inventory Service, Coupon Service, Payment Service, Delivery Service
Reference Document
Created By |  | Yi Yi Htun
Date of Creation |  | 21/05/2025
Date of Review
Module 1: Inventory Service
Test Case ID | Scenario ID | Test Case Scenario | Test Case | Pre-Conditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Severity | Priority | Notes | Tested By | Comments
TC_1 | FUN_INV_1 | Verify adding a new product to inventory | Add a new product and confirm it's listed in the inventory | Admin or seller logged in with permissions | 1. Go to inventory module 2. Click 'Add Product' 3. Fill in product details 4. Submit | Product Name: T-Shirt Stock: 100 Price: 300 THB | Product appears in inventory list with correct details |  | Not Executed | High | High
TC_2 | FUN_INV_2 | Verify that stock quantity can be modified correctly (increase/decrease) | Modify stock quantity and verify the update reflects | Product exists in inventory | 1. Go to product 2. Click 'Edit' 3. Change stock quantity 4. Save changes | Change stock from 100 to 150 | Stock updated successfully to 150 |  | Not Executed | Medium | High
TC_3 | FUN_INV_3 | Validate that changes are reflected in real-time inventory records | Check inventory after stock update from another interface | Inventory is accessible via admin and API | 1. Update stock via API 2. Check UI inventory | Stock updated via API to 120 | UI displays updated stock instantly (120) |  | Not Executed | High | High
TC_4 | FUN_INV_4 | Verify product details in inventory | Confirm product attributes like name, SKU, price are stored and displayed correctly | Product added to inventory | 1. View product in inventory 2. Check displayed attributes | Name: T-Shirt, SKU: TS001, Price: 300 THB | Details displayed correctly as entered |  | Not Executed | Medium | Medium
TC_5 | FUN_INV_5 | Validate removal of a product from inventory | Delete a product and confirm it no longer appears | Product exists in inventory | 1. Locate product 2. Click 'Delete' 3. Confirm action | Product ID: 12345 | Product removed from inventory list |  | Not Executed | High | High
TC_6 | FUN_INV_6 | Verify inventory adjustment operations | Perform adjustment and validate logs and final stock | User with adjustment permissions | 1. Select product 2. Click 'Adjust Inventory' 3. Enter adjustment value 4. Submit | Adjust +10 units | Inventory updated and adjustment logged |  | Not Executed | Medium | Medium
TC_7 | FUN_INV_7 | Verify inventory is decremented only after order confirmation | Ensure stock is only reduced after confirmed payment | Product in stock, order placed but not confirmed | 1. Place order 2. Check inventory 3. Confirm order 4. Check inventory again | Order quantity: 1 | Stock decremented only after order confirmation |  | Not Executed | High | High
TC_8 | FUN_INV_8 | Ensure inventory rollback if payment or downstream service fails | Trigger failure after stock decrement and verify rollback | Order processing system integrated with payment and inventory | 1. Place order 2. Confirm payment fails 3. Check inventory | Simulated payment failure | Inventory restored to original state |  | Not Executed | Critical | High
TC_9 | NON-FUN_INV_9 | Verify a high volume of simultaneous inventory update requests from multiple shops | Simulate multiple concurrent updates and check consistency | Multiple shops managing shared stock | 1. Send concurrent updates 2. Check final stock and logs | 10 simultaneous update requests | No conflicts or data loss; final stock is accurate |  | Not Executed | Critical | High
TC_10 | NON-FUN_INV_10 | Verify system performance under delivery tracking load | Stress test delivery tracking API under load | Tracking system online | 1. Simulate 1000 tracking requests per minute 2. Measure response time and error rate | 1000 delivery IDs | 95% responses < 2s, minimal error rate |  | Not Executed | High | Medium
Module 2: Coupon Service
Test Case ID | Scenario ID | Test Case Scenario | Test Case | Pre-Conditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Severity | Priority | Notes | Tested By | Comments
TC_11 | FUN_COUPON_11 | Verify that users can successfully collect vouchers from the homepage, campaign banners, product pages, or promotional pop-ups. | Ensure users can collect vouchers from homepage, banners, product pages, and pop-ups | Voucher campaign active | 1. Navigate to homepage/campaign banner/product page/pop-up 2. Click 'Collect Voucher' | User ID: 1001 | Voucher is added to the user's wallet |  | Not Executed | High | High
TC_12 | FUN_COUPON_12 | Verify that users receive a coupon/voucher immediately after following a shop, if such a promotion is active. | Ensure voucher is granted immediately after following a shop | Follow-to-redeem promotion active | 1. Follow shop 2. Check voucher wallet | Shop ID: S123 | Voucher is available in wallet immediately |  | Not Executed | Medium | High
TC_13 | FUN_COUPON_13 | Verify that claimed vouchers are immediately visible and usable from the user's voucher wallet. | Claim voucher and verify its presence and usability in voucher wallet | User has collected a voucher | 1. Open voucher wallet 2. Verify claimed voucher is listed | Voucher Code: WEL123 | Voucher is usable and listed in the wallet |  | Not Executed | Medium | Medium
TC_14 | FUN_COUPON_14 | Verify special welcome voucher for new users | Ensure new users receive a special welcome voucher | User account created today | 1. Register new user 2. Check voucher wallet | User Type: New | Welcome voucher is issued |  | Not Executed | Medium | High
TC_15 | FUN_COUPON_15 | Verify frontend display of voucher conditions matches backend configuration e.g Min. Spend THB 1,500 • Valid Until May 31, 2025 • LazMall Only | Ensure displayed conditions match backend config | Voucher configured in backend | 1. View voucher on frontend 2. Compare with backend config | Min Spend: 1500 THB, Valid Until: May 31, LazMall Only | Frontend displays conditions accurately |  | Not Executed | High | Medium
TC_16 | FUN_COUPON_16 | Validate that a valid voucher/Coupon code is successfully applied and the discount is reflected in the total price | Apply valid voucher code and verify discount | Voucher is valid and applicable | 1. Add items to cart 2. Apply voucher 3. Check discount | Voucher Code: SAVE100 | Discount applied to total price |  | Not Executed | High | High
TC_17 | FUN_COUPON_17 | Validate that free shipping vouchers waive shipping fees under specified conditions (e.g., minimum purchase amount, eligible regions). | Apply free shipping voucher and verify zero shipping fees | Free shipping voucher collected | 1. Add qualifying items to cart 2. Apply voucher 3. Proceed to checkout | Voucher Code: FREESHIP | Shipping fee is waived |  | Not Executed | Medium | Medium
TC_18 | FUN_COUPON_18 | Validate that an expired voucher code is rejected with an appropriate error message | Apply expired voucher and verify error | Voucher past expiration | 1. Attempt to apply expired voucher | Voucher Code: EXPIRED01 | Error message: 'Voucher expired' |  | Not Executed | Medium | Medium
TC_19 | FUN_COUPON_19 | Verify that such vouchers are only applicable to products belonging to the respective store or seller during checkout. | Verify voucher only works with eligible store items | Store-specific voucher in wallet | 1. Add non-eligible items 2. Apply voucher | Voucher Code: STOREONLY | Voucher not applicable to ineligible items |  | Not Executed | High | Medium
TC_20 | FUN_COUPON_20 | Ensure that eligible coupons can be manually by keyin the coupon code to the order. | Enter coupon code manually and apply | User has valid coupon code | 1. Go to checkout 2. Enter code manually 3. Apply | Coupon Code: MANUAL100 | Discount applied successfully |  | Not Executed | Medium | Medium
TC_21 | FUN_COUPON_21 | Verify that removing an applied voucher restores it to the user's voucher wallet | Remove applied voucher and check if restored to wallet | Voucher applied to cart | 1. Remove applied voucher 2. Check voucher wallet | Voucher Code: TEMP100 | Voucher reappears in wallet |  | Not Executed | Medium | Medium
TC_22 | FUN_COUPON_22 | Validate that when a user removes an existing voucher and applies a new one, the updated voucher is correctly applied and reflected in the order summary. | Remove existing voucher and apply a new one | Two vouchers in wallet | 1. Apply Voucher A 2. Remove Voucher A 3. Apply Voucher B 4. Check summary | Voucher A: OLD10, Voucher B: NEW20 | New voucher applied correctly |  | Not Executed | Medium | Medium
TC_23 | FUN_COUPON_23 | Confirm that the correct discount or benefit is reflected in the order summary. | Ensure all benefits from voucher appear in final order | Voucher successfully applied | 1. Review order summary after applying voucher | Voucher: 20%OFF | Order summary includes 20% discount |  | Not Executed | High | High
TC_24 | FUN_COUPON_24 | Ensure that once a coupon has expired, it is automatically removed from the list of selectable vouchers in the user's voucher wallet or checkout screen | Ensure expired coupons disappear from wallet/checkout | Expired voucher in backend | 1. Open voucher wallet or checkout 2. Verify voucher is gone | Voucher Code: OLDCOUPON | Expired coupon not listed |  | Not Executed | Medium | Medium
TC_25 | Non-FUN_COUPON_25 | Verify for high load of Coupon (e.g., 11.11 sales event/ 10:10 sales) | Simulate high load redemption (e.g., 11.11) | Coupon available with limited redemptions | 1. Simulate 5,000 concurrent redemptions | Coupon Code: HOTDEAL11 | System remains stable, max redemption limit enforced |  | Not Executed | Critical | High
TC_26 | Non-FUN_COUPON_26 | Simulate 5,000 users attempting to redeem the same coupon code concurrently to validate system performance and redemption limits. | Validate system performance and enforce redemption limits under high-load concurrent coupon redemption | Coupon is active with a set redemption limit (e.g., 1,000 uses). Load testing tools available. | 1. Simulate 5,000 concurrent users applying the same coupon code via test environment. 2. Monitor system response time and behavior. 3. Capture logs and error reports. | Coupon Code: FLASH500 Redemption Limit: 1,000 Concurrent Users: 5,000 | Only first 1,000 redemptions succeed. System remains stable with minimal latency. Errors or throttling handled gracefully for excess requests. |  |  | Critical | High | Ensure logging, throttling, and queuing mechanisms are in place.
Module 3: Payment Service
Test Case ID | Scenario ID | Test Case Scenario | Test Case | Pre-Conditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Severity | Priority | Notes | Tested By | Comments
TC_27 | FUN_PAYMENT_27 | Verify successful payment processing with valid card | Test to verify successful payment processing with valid card | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify successful payment processing with valid card - Expected behavior validated |  | Not Executed | Medium | High
TC_28 | FUN_PAYMENT_28 | Validate error on invalid card details | Test to validate error on invalid card details |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Validate error on invalid card details - Expected behavior validated |  | Not Executed | Medium | Medium
TC_29 | FUN_PAYMENT_29 | Verify duplicating transaction (Ensure no double charge on repeat click) | Test to verify duplicating transaction (ensure no double charge on repeat click) |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify duplicating transaction (Ensure no double charge on repeat click) - Expected behavior validated |  | Not Executed | Medium | Medium
TC_30 | FUN_PAYMENT_30 | Allow retry if first attempt fails due to timeout | Test to allow retry if first attempt fails due to timeout |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Allow retry if first attempt fails due to timeout - Expected behavior validated |  | Not Executed | High | Medium
TC_31 | FUN_PAYMENT_31 | Verify refund processed correctly | Test to verify refund processed correctly |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify refund processed correctly - Expected behavior validated |  | Not Executed | Medium | High
TC_32 | FUN_PAYMENT_32 | Verify Payment Summary or Checkout Page Displays Correct Data | Test to verify payment summary or checkout page displays correct data | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Payment Summary or Checkout Page Displays Correct Data - Expected behavior validated |  | Not Executed | Medium | High
TC_33 | FUN_PAYMENT_33 | Verify All Available Payment Methods Are Displayed in the Drop-Down List | Test to verify all available payment methods are displayed in the drop-down list | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify All Available Payment Methods Are Displayed in the Drop-Down List - Expected behavior validated |  | Not Executed | Medium | High
TC_34 | FUN_PAYMENT_34 | Verify Mobile Banking Option Supports All Thai Banks | Test to verify mobile banking option supports all thai banks |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Mobile Banking Option Supports All Thai Banks - Expected behavior validated |  | Not Executed | Medium | Medium
TC_35 | FUN_PAYMENT_35 | Verify QR PromptPay Payment Flow | Test to verify qr promptpay payment flow | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify QR PromptPay Payment Flow - Expected behavior validated |  | Not Executed | Medium | High
TC_36 | FUN_PAYMENT_36 | Verify Payment Using Lazada Wallet | Test to verify payment using lazada wallet | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Payment Using Lazada Wallet - Expected behavior validated |  | Not Executed | Medium | High
TC_37 | FUN_PAYMENT_37 | Verify Payment via TrueMoney | Test to verify payment via truemoney | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Payment via TrueMoney - Expected behavior validated |  | Not Executed | Medium | High
TC_38 | FUN_PAYMENT_38 | Verify LINE Pay Integration | Test to verify line pay integration |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify LINE Pay Integration - Expected behavior validated |  | Not Executed | Medium | Medium
TC_39 | FUN_PAYMENT_39 | Verify Cash on Delivery Option | Test to verify cash on delivery option |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Cash on Delivery Option - Expected behavior validated |  | Not Executed | Medium | Medium
TC_40 | FUN_PAYMENT_40 | Verify Cash on Delivery | Test to verify cash on delivery |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Cash on Delivery - Expected behavior validated |  | Not Executed | Medium | Medium
TC_41 | FUN_PAYMENT_41 | Verify Receipt Is Successfully Sent to the Use | Test to verify receipt is successfully sent to the use |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Receipt Is Successfully Sent to the Use - Expected behavior validated |  | Not Executed | Medium | Medium
TC_42 | FUN_PAYMENT_42 | Attempt payment with expired card | Test to attempt payment with expired card | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Attempt payment with expired card - Expected behavior validated |  | Not Executed | Medium | High
TC_43 | FUN_PAYMENT_43 | Leave mandatory field empty and try to proceed | Test to leave mandatory field empty and try to proceed |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Leave mandatory field empty and try to proceed - Expected behavior validated |  | Not Executed | Medium | Medium
TC_44 | FUN_PAYMENT_44 | Try payment with negative amount | Test to try payment with negative amount | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Try payment with negative amount - Expected behavior validated |  | Not Executed | Medium | High
TC_45 | FUN_PAYMENT_45 | Try payment with zero amount | Test to try payment with zero amount | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Try payment with zero amount - Expected behavior validated |  | Not Executed | Medium | High
TC_46 | FUN_PAYMENT_46 | Let session expire before submitting payment | Test to let session expire before submitting payment | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Let session expire before submitting payment - Expected behavior validated |  | Not Executed | Medium | High
TC_47 | FUN_PAYMENT_47 | Submit payment when payment service is offline | Test to submit payment when payment service is offline | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Submit payment when payment service is offline - Expected behavior validated |  | Not Executed | Medium | High
TC_48 | NON-FUN_PAYMENT_48 | Verify that the application displays a clear error or retries the request appropriately when the payment gateway times out (e.g., after 10 seconds of no response). | Test to verify that the application displays a clear error or retries the request appropriately when the payment gateway times out (e.g., after 10 seconds of no response). | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify that the application displays a clear error or retries the request appropriately when the payment gateway times out (e.g., after 10 seconds of no response). - Expected behavior validated |  | Not Executed | Medium | High
TC_49 | NON-FUN_PAYMENT_49 | Ensure that the payment service can handle a high number of concurrent payment attempts without race conditions or double charges. | Test to ensure that the payment service can handle a high number of concurrent payment attempts without race conditions or double charges. | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Ensure that the payment service can handle a high number of concurrent payment attempts without race conditions or double charges. - Expected behavior validated |  | Not Executed | Medium | High
TC_50 | NON-FUN_PAYMENT_50 | Conduct load testing to validate that the payment service can process a high volume of requests (e.g., 1,000 transactions per minute) | Test to conduct load testing to validate that the payment service can process a high volume of requests (e.g., 1,000 transactions per minute) | User is on checkout page with items in cart | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Conduct load testing to validate that the payment service can process a high volume of requests (e.g., 1,000 transactions per minute) - Expected behavior validated |  | Not Executed | Medium | High
TC_51 | NON-FUN_PAYMENT_51 | Verify Security - no card inforamtion are stored in the system | Test to verify security - no card inforamtion are stored in the system |  | 1. Proceed to checkout 2. Select payment method 3. Enter required information 4. Submit | Sample card, voucher, user session, etc. | Verify Security - no card inforamtion are stored in the system - Expected behavior validated |  | Not Executed | High | Medium
Module 4: Delivery Service
Test Case ID | Scenario ID | Test Case Scenario | Test Case | Pre-Conditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Severity | Priority | Notes | Tested By | Comments
TC_52 | FUN_DEL52 | Verify delivery date and address are correct after made the payment | Test to verify delivery date and address are correct after made the payment | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify delivery date and address are correct after made the payment - System behaves as expected |  | Not Executed | Medium | High
TC_53 | FUN_DEL53 | Allow users to modify the delivery address before the order is dispatched. | Test to allow users to modify the delivery address before the order is dispatched. | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Allow users to modify the delivery address before the order is dispatched. - System behaves as expected |  | Not Executed | Medium | High
TC_54 | FUN_DEL54 | Ensure that once an order is confirmed, a delivery partner is assigned correctly. | Test to ensure that once an order is confirmed, a delivery partner is assigned correctly. | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Ensure that once an order is confirmed, a delivery partner is assigned correctly. - System behaves as expected |  | Not Executed | Medium | High
TC_55 | FUN_DEL55 | Validate real-time tracking updates (e.g., Shipped, In Transit, Delivered). | Test to validate real-time tracking updates (e.g., shipped, in transit, delivered). |  | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Validate real-time tracking updates (e.g., Shipped, In Transit, Delivered). - System behaves as expected |  | Not Executed | Medium | High
TC_56 | FUN_DEL56 | Ensure the system manages failed deliveries (e.g., customer not available) and allows rescheduling. | Test to ensure the system manages failed deliveries (e.g., customer not available) and allows rescheduling. |  | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Ensure the system manages failed deliveries (e.g., customer not available) and allows rescheduling. - System behaves as expected |  | Not Executed | High | Medium
TC_57 | FUN_DEL57 | Verify the Notification of Delivery Progress (e.g SMS, push, or email notifications are sent for each status update.) | Test to verify the notification of delivery progress (e.g sms, push, or email notifications are sent for each status update.) | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify the Notification of Delivery Progress (e.g SMS, push, or email notifications are sent for each status update.) - System behaves as expected |  | Not Executed | Medium | High
TC_58 | FUN_DEL58 | Verify that cancelling an order cancels the associated delivery and updates logistics records. | Test to verify that cancelling an order cancels the associated delivery and updates logistics records. | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify that cancelling an order cancels the associated delivery and updates logistics records. - System behaves as expected |  | Not Executed | Medium | High
TC_59 | FUN_DEL59 | Verify that deliver pick up for return items | Test to verify that deliver pick up for return items |  | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify that deliver pick up for return items - System behaves as expected |  | Not Executed | Medium | Medium
TC_60 | FUN_DEL60 | Verify Priority 24H Delivery Option | Test to verify priority 24h delivery option | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify Priority 24H Delivery Option - System behaves as expected |  | Not Executed | Medium | High
TC_61 | FUN_DEL61 | Check with Seller to follow up on the delivery process | Test to check with seller to follow up on the delivery process | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Check with Seller to follow up on the delivery process - System behaves as expected |  | Not Executed | Medium | High
TC_62 | FUN_DEL62 | Validate for wrong address : user enters an address with missing fields (e.g., no postal code, symbols in street name). | Test to validate for wrong address : user enters an address with missing fields (e.g., no postal code, symbols in street name). |  | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Validate for wrong address : user enters an address with missing fields (e.g., no postal code, symbols in street name). - System behaves as expected |  | Not Executed | High | Medium
TC_63 | FUN_DEL63 | Verify for Changing Address After Shipment | Test to verify for changing address after shipment |  | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify for Changing Address After Shipment - System behaves as expected |  | Not Executed | Medium | Medium
TC_64 | NON-FUN_DEL64 | Test if delivery API performs well under 1000+ concurrent delivery requests | Test to test if delivery api performs well under 1000+ concurrent delivery requests | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Test if delivery API performs well under 1000+ concurrent delivery requests - System behaves as expected |  | Not Executed | Medium | High
TC_65 | NON-FUN_DEL65 | Verify that 1000+ delivery status push noti are sent at a time | Test to verify that 1000+ delivery status push noti are sent at a time | Order placed and payment completed | 1. Initiate order process 2. Proceed through delivery flow 3. Observe system behavior | Sample user, address, tracking ID, status, order ID, etc. | Verify that 1000+ delivery status push noti are sent at a time - System behaves as expected |  | Not Executed | Medium | High

## Test Execution Summary
TEST CYCLE 1
| Total TCs | Not Executed | Pass | Fail | Not Completed | SUM
Release # :
Module 1 : Inventory Service | 10
Module 2 : Coupon Service | 16
Module 3 : Payment Service | 25
Module 4 : Delivery Service | 14
TOTAL | 65

## Defect Log Traker
Project Name
Devices Used
Build Details
DEFECT LOG TRACKER
Defect ID | Summary | Description | Module | Sub-Module | Reported By | Reported Date | Steps to Reproduce | Environment | Severity | Priority | Assigned To | Status | Resolution | Comments
DL-001 | [8 empty] | Low | Low |  | New | Not Reproducible
DL-002
DL-003
DL-004
DL-005
DL-006
DL-007
DL-008
DL-009
DL-010